## 23 Jul 2021 export
[30 empty] | Aug | [30 empty] | Sep | [31 empty] | Oct | [30 empty] | Nov
|  |  | 2021-07-19 |  |  | 2021 W30 | [6 empty] | 2021 W31 | [6 empty] | 2021 W32 | [6 empty] | 2021 W33 | [6 empty] | 2021 W34 | [6 empty] | 2021 W35 | [6 empty] | 2021 W36 | [6 empty] | 2021 W37 | [6 empty] | 2021 W38 | [6 empty] | 2021 W39 | [6 empty] | 2021 W40 | [6 empty] | 2021 W41 | [6 empty] | 2021 W41 | [6 empty] | 2021 W42 | [6 empty] | 2021 W43 | [6 empty] | 2021 W44 | [6 empty] | 2021 W45 | [6 empty] | 2021 W46 | [6 empty] | 2021 W47 | [6 empty] | 2021 W48 | [6 empty] | 2021 W49 | [6 empty] | 2021 W50 | [6 empty] | 2021 W51 | [6 empty] | 2021 W52 | [6 empty] | 2022 W1 | [6 empty] | 2022 W2 | [6 empty] | 2022 W3 | [6 empty] | 2022 W4 | [6 empty] | 2022 W5 | [6 empty] | 2022 W6 | [6 empty] | 2022 W7 | [6 empty] | 2022 W8 | [6 empty] | 2022 W9 | [6 empty] | 2022 W10 | [6 empty] | 2022 W11
| Display Week: |  | 1 |  |  | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14
 | time axis 2021-07-19 to 2022-03-20
TASK | Duration (days) | PROGRESS | START | END | DAYS | time axis 2021-07-19 to 2022-03-20
ETN Members Consortium
Commitment agreement |  |  |  | 2021-08-01
Budget Finalisation | 9 |  | 2021-07-23 | 2021-07-31 | 9
NDA | 31 |  | 2021-08-01 | 2021-08-31
Project Public Start | 1 |  | 2021-09-01 | 2021-09-01
Invoicing 1/3 - powder (15k€) | 1 |  | 2021-09-11 | 2021-09-11 | 1
Invoicing 2/3 - build jobs (5k€) | 1 |  | 2021-10-21 | 2021-10-21
Invoicing 3/3 - final report for review (5k€) | 1 |  | 2021-11-26 | 2021-11-26
Powder
Powder order @ Oerlikon | 1 |  | 2021-08-01 | 2021-08-01
Powder delivery @ 3rd Party - Project Management | 42 |  | 2021-08-01 | 2021-09-11
Powder delivery - buffer | 15 |  | 2021-09-11 | 2021-09-25
Powder delivery @ L-PBF Machine OEM | 5 |  | 2021-09-18 | 2021-09-22
L-PBF Machines OEMs
Commitment formalisation |  |  |  | 2021-08-01
NDA | 31 |  | 2021-08-01 | 2021-08-31 | 31
Parts production | 30 |  | 2021-09-22 | 2021-10-21 | 30
3rd Party - Testing
Testing Programme | 35 |  | 2021-10-07 | 2021-11-10
EPRI testing - PCRT (non-destructive) | 35 |  | 2021-10-07 | 2021-11-10
3rd Party - Project Management
Agreement with ETN | 1 |  | 2021-08-01 | 2021-08-01 | 1
NDA coordination | 31 |  | 2021-08-01 | 2021-08-31 | 31
Parts production witnessing | 30 |  | 2021-09-22 | 2021-10-21 | 30
Parts delivery to 3rd Party - Testing | 30 |  | 2021-10-02 | 2021-10-31
Testing programme coordination and witnessing | 35 |  | 2021-10-07 | 2021-11-10 | 35
Results consolidation and documentation | 15 |  | 2021-11-11 | 2021-11-25 | 15
Report delivery (for review) | 1 |  | 2021-11-26 | 2021-11-26
[19 empty] | Partners NDA | [40 empty] | Powder delivery | [25 empty] | Testing Programme | [34 empty] | Report prep
Parts production and delivery
Report delivery